Effective Date: Jan 5, 2026

Last Update Date: [Date]

Table of Contents

1. Introduction & Scope	1

2. Teams and Responsibilities	1

3. Teams Interactions	3

4. Important dates	5

5. Service Level Agreements and Expected Standards	6

5.1. Trial owners' services	6

5.2. Data team services	8

5.3. Inventory team services	11

5.4. Laboratory team services	12

5.5. Station trials team’s services	13

5.6. Field trials teams’ services	14

6. Communication and Additional SLAs	15

7. Escalation Procedure	16

8. Review and Amendment	16

9. Signatures	17

#### 1. Introduction & Scope

This Service Level Agreement (SLA) outlines the performance metrics, responsibilities, and escalation procedures for all intra-departmental service provision by sub-teams within the Agricultural Innovations Department. This includes the expectations of project management, in particular that of trial owners, who provide a service to the department, and in many cases, additionally to other departments (who made the request or are stakeholders). The purpose of this SLA is to ensure clear communication, efficient collaboration, and high-quality outcomes in the development, execution, and analysis of agricultural research.

#### 2. Teams and Responsibilities

2.1. Trial Owners (Project management)

- Develop trial plans, clear and detailed trial implementation (translated if necessary), and measurement protocols.

- Source seeds and special materials (measurement or trial supplies) that will be needed along the trial.

- Organize trial-specific training that includes objectives, protocols, and measurements for implementing teams.

- Provide datasheets to the station team, including plot randomization.

- For on-farm trials, align with the data team on measurements and review data sheet drafts from the data team.

- Prepare inputs packaging instructions to the Lab or Inventory teams.

- Provide timely feedback on trial progress reports and reported issues.

- Conduct field visits in different trial periods at different locations for timely feedback to the implementing team.

- Compile findings into trial reports and engage with scaling channels to facilitate the dissemination of results.

2.2. Station Trials Team (Implementing)

- Execute trials according to agreed-upon protocols on research stations.

- Ensure proper rotations, blocking, plot layouts, planting, plants management, and harvesting practices are used.

- Collect accurate quantitative/qualitative data based on the prescribed data collection moments in the protocols.

- Maintain detailed trial records and observation logs.

- Report any deviations or issues immediately to the Trial Owners.

- Ensure each station has adequate and calibrated regular measurement tools.

- Matching labor availability with the trials demand.

2.3. On-Farm Trials Team (Implementing)

- Recruit representative trial participants from the ME/AEZs in which the trials are planned.

- Conduct farmers’ training and guide them in all activities during the trial implementation.

- Collect qualitative and quantitative data for each trial according to the protocols and measurement periods.

- Ensure each Officer has a functioning tablet and that collected data are submitted immediately.

- Collect soil/plant samples and submit them to the INN Laboratory.

- Address farmers’ concerns and provide technical support.

- Report any deviations or issues immediately to the Trial Owners.

- Ensure weather sensors are installed in safe places and any incident is reported and addressed as soon as possible.

- Ensure each Officer has adequate and calibrated regular measurement tools.

- Matching labor availability with the trials demand.

2.4. Data Team (Supporting)

- Design and provide data collection tools to the field trials team.

- Assist in trial materials translations as requested by Trial Owners.

- Develop and maintain robust data dashboards for trial data.

- Monitor, validate, and clean raw trial data collected by the field trials team.

- Maintain and track the functionality of weather sensors and integrate weather data into trial data.

- Perform trial data analysis and advanced machine learning analyses as per requests from Trial Owners.

2.5. Inventory Team (Supporting)

- Forecast and source regular trial supplies or measurement tools to ensure the minimum stock quantity is kept.

- Manage the inventory of trial materials (seeds, chemicals, consumables, tools, etc.)

- Distribute materials to trial teams as per requests (coordinators and trial owners).

- Maintain laboratory equipment and conduct calibration of INN regular measurement materials.

2.6. Laboratory Team (Supporting + Implementing)

- Receive, process, and analyze samples (compost, soil, and plant) accurately and efficiently.

- Provide accurate and timely soil/plant samples' analytical results.

2.7. High-touch Extension Team (Implementing + Scaling channel)

- Scale cropping systems & farm system design prototypes through high-touch extension agents.

- Deliver high-quality training to HTE agents on scaled farming practices.

- Develop and use training mechanisms that enable effective knowledge and capability transfer.

- Manage exemplary Mother-farms to showcase the performance of scaled cropping systems.

- Monitor & provide annual reports on the adoption and performance of scaled systems through HTE Agents.

#### 3. Interactions between teams

Successful trial development and implementation involves the collaboration of multiple teams besides the Trial Owner and the Implementing team (station or field trials team). As indicated by the section above, one trial involves at least 3-4 parties, depending on whether it is implemented at the station (Trial owner, Lab & Inv., Station) or on-farm (Trial owner, Lab & Inv., Data team, Field trials team).

For example, adequate fulfillment of responsibilities by the trial developing party doesn’t guarantee smooth implementation by the implementing party if the supporting party didn’t fulfill its role adequately. Similarly, the supporting party won’t fulfill its mandate (i.e, serving the implementing party) if the developer party doesn’t perform its role adequately. Also, adequate fulfillment of the developer's part and the supporting party doesn’t guarantee high-quality implementation of the trial unless the system provides a way to hold the implementing team accountable. The multi-lateral nature of INN teams’ interactions (interactions between three parties) requires that the Service Level Agreement between INN teams enable each team to be held accountable (mutual responsibility and accountability).

Interactions between two teams are a set of services provided by one party (A) to the other (B) for the other party (B) to fulfill its mandate (i.e, serving party C). To illustrate the mutual responsibility and accountability between teams, interactions between teams are identified and mapped (fig. 1), and a 2) a service level agreement is developed for each service provided by a team, including the scope of the service, the client’s responsibilities for obtaining the service, the highest level of service if the client has fulfilled their responsibilities and what should be be expected by the client (requestor) if they fail to fulfill their responsibilities.

The figure below maps the interactions between sub-teams, and the arrow’s direction indicates the served party.

Trial Owners

Field Trials Team

Data Team

Inventory

Laboratory

Station Team

HTE |

Scaling Channels

Fig 1. Schematic presentation of INN teams' interactions

The services provided by each team and the clients for each service are summarized in the table below:

| Serving party | Service | Client |
| --- | --- | --- |
| Trial Owners | Trial planning and oversight | INN Department or other requesting department |
|  | Phase 0 analysis and stakeholder alignment | INN Department |
|  | Results compilation and dissemination | INN Department/Scaling channels |
| Data team | Data collection materials development | Field Trials Team/Trial Owners |
|  | Data quality monitoring | Field Trials Team |
|  | Weather data monitoring | Field Trials Team/Station team/Trial Owners |
|  | Data processing and analysis | Trial Owners |
|  | IT Equipment sub-inventory management | INN Department |
|  | Survey Implementation | Trial Owners |
| Inventory and Laboratory Teams | Inventory management | Station/Field Trials teams/Laboratory/Trial Owners |
|  | Inputs sourcing and packaging | Trial Owners |
|  | Compost, Soil, and Plant Analysis | Trial Owners |
| Station and Field trials teams | Trial implementation | Trial owners |

#### 4. Important dates

Effective collaboration between INN teams relies on each party aligning its operations with the INN trial planning calendar. The table below indicates the standard dates for specific events that determine the quality of smooth season preparation, as they are indicated by the calendar. INN staffers commit to ensuring these events happen by the indicated dates!

| No | Event | A Season Date | B Season Date | C Season Date |
| --- | --- | --- | --- | --- |
| 1 | Sharing the list of varieties/imported items sourced through Global Sourcing (seed + non-ag) | 5-Jan | NA | NA |
| 2 | Completing Trial Summary Info (Treatments finalization) | 15-Apr | 15-Oct | 15-Feb |
| 3 | Inputs calculation completion | 30-Apr | 30-Oct | 20-Feb |
| 4 | Final alignment with the implementing team on the trial plan | 30-Jun | 25-Nov | 15-Mar |
| 6 | Develop the Methods and Measurements | 30-Jun | 25-Nov | 15-Mar |
| 7 | Alignment with the implementing/Data team on the variables to measure | 20-Jul | 20-Dec | 5-Apr |
| 8 | Input packaging starts | 5-Aug | 5-Jan | 20-Apr |
| 9 | Inputs distribution – Station | 15-Aug | 15-Jan | 30-Apr |
| 13 | Inputs distribution – On-farm | 15-Aug | 15-Jan | 30-Apr |
| 14 | SLA compliance feedback | 30-May | 30-Oct | 30-Oct |

* in case there is a discrepancy between the above table and the calendar linked above, the latter is the source of truth.

#### 5. Service Level Agreements and Expected Standards

##### 5.1. Trial owners' services

Service 1: Trial planning and oversight

Client: INN Department or other requesting department

| Task | Expectation | Client’s responsibilities | Highest level of Service quality |
| --- | --- | --- | --- |
| Trials planning | Alignment with the implementing team on the trial plan using completed information in the Trial plans document - ex, treatments, plot size, sample size, exp. design, locations, season, etc - After this step, the field team starts farmers' mobilization. | - The trial owner bears all responsibilities - Specific trials needed by other departments must be requested at least 6 months in advance of the season start, and are subject to bandwidth constraints. On rare occasions, non-INN staff may be designated as Trial owners, but they must agree to all responsibilities in this SLA. | Completing the trial plans by: April 15 (A Season); October 15 (B Season); February 15 (C Season). |
| Measurements determination | Alignment with the implementing team on the list of variables planned to be measured, measurement time, method, and tools. This provides an opportunity to become familiar with the special measurements and tools that will be required. |  | Methods and Measurements are developed by: June 30 (A Season); November 25 (B Season); March 15 (C Season); |
| Protocols development | This primarily involves the implementation details, including participant information, field conditions, land preparation, soil/plant sampling, planting, input rates and application times, harvesting, and other relevant aspects. |  | Protocol delivered to implementing teams in 2 Weeks before the trial period starts or the activity implementation |
| Data collection sheets and treatment randomization - Station | Final datasheet approved by the Station team Coordinator |  | The datasheet is complete (100%) in 5 days before the trial starts |
| Trial review meeting with the Data team - On-farm Trials | An informative session for the Data team on the variables to be measured, their measurement methods, and the measurement period is conducted before the season or trial period begins. |  | An alignment meeting is conducted in 4 weeks before the trial begins: July 20 (A Season); January 5 (B Season); April 15 (C Season). |
| Inputs (OR Tools under evaluation) sourcing | All inputs, except those sourced from LOG or the tool under evaluation, such as farming tools, are delivered to the Inn WH in sufficient time to allow for germination testing and packaging. |  | - Inputs calculation completed by: April 30th (A Season); October 30th (B Season); February 28th (C Season). - Inputs and special trial supplies are delivered to the WH by: Aug 5th (A Season); January 5th (B Season); April 20th (C Season). |
| Special trial supplies sourcing | Non-regular consumables: irrigation water, mulch, gloves, tiny sachets for veggie seeds, etc., are delivered to the Inn WH before being used by the Inventory team or Trial implementation team. |  |  |
| Special measurement materials sourcing | Irregular measurement tools (not scales, grain moisture meters, and measuring tapes) are sourced on time before they are used, and early enough to allow the team to be trained on the tool before it is used. |  | The material is delivered 10 days before the measurement time OR 3 days before the monthly Field team meeting |
| Protocol and datasheets review sessions | Organizing protocol and data sheets review sessions with the Data team or the Implementing teams, per trial period |  | Protocols and datasheets review sessions are held 5 days before the trial period starts. |

Service 2: Phase 0 analysis and stakeholder alignment

Client: INN Department

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Project charter & critical path | Charter should a) examine whether there is an impact case for the project based on provided objectives (from requestor or department leadership); b) propose an initial list of technology options to be tested; and c) propose target clients/scaling channels. | The trial owner bears all responsibilities | Phase 0 report of the studied crop is provided within 3 months, or as aligned with the manager in the critical path. | NA |
| Presentation-based alignment with stakeholders | Presenting the Phase 0 findings to stakeholders for consensus on the current challenges to be addressed |  | Presentation is delivered | NA |

Service 3: Results compilation and dissemination

Client: INN Department/Scaling channels (HTE or Tubura channels)

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Incremental and final reports | Use of the correct reporting template. Ensure the report is peer-reviewed | Peer review and providing feedback within 10 business days max after the trial owner shares the report | The trial report is completed in 12 weeks after the trial completion | The reports will be shared in their draft version |
| Updating: Google Drive “Themes” folder + Report tracker + Global Knowledge Hub | - Adding the report, results, and PPT files to the Report tracker - Updating the Google Drive folder in alignment with SOP | NA | The Google Drive Folder and Report tracker are complete in 1 day after the draft version. The knowledge hub is completed in 1 day after addressing the INN Lead comments in the report. | NA |
| Presentation of findings and recommendations to stakeholders | Should include a recommendation tool, marketing proposal, and/or extension material in correct format required by scaling channel, where relevant. | NA | Findings are presented to stakeholders in 4 weeks after report completion. | NA |

##### 5.2. Data team services

Service 1: Data collection materials development

Client: Field Trials Team/Trial Owners

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Questionnaire design and explanations | Alignment with FTT on the questions’ wording, sequence, skip conditions, and questionnaire versions | - An alignment meeting is conducted in 4 weeks before the trial begins or 2 weeks before each trial period (if not covered in the trial review meeting) - The Trial Owner provides feedback within 2 days max after receiving the questionnaire draft - FFT Organize the datasheet review meeting and share errors found with the DT 2 days before data collection starts. | The data collection sheet (Form) draft is shared with the FTT 5 days before the data collection starts. | The final version of the datasheet is shared, but after the data collection period has reached |
| Packages randomization lists for Tricot trials | Generating and sharing the lists used during input packaging and scannable labels for farmers' registration | Sharing the final list of available varieties in that trial | The package list is shared 5 days before the seeds are packaged | The list is provided while the seed packaging is started |
| Validated and Non-validated farmers' list for Tricot trials | Generate and share the lists that indicate the farmers for which quantitative yield data will be collected for the drying harvest | No special requirement besides aligning with the trial owner on the rate of validated farmers | The list is provided 4 weeks before harvest begins | - |

Service 2: Data quality monitoring

Client: Field Trials Team

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Data submission dashboards | Number of submissions per form and Officer regularly | Communication that the trial has started, and this is done once | The data submission dashboard is shared Weekly on Monday Except in P2 DV period | - |
| Data quality dashboards | Erroneous values submitted in each form at a specific stage of the Form's data collection | None | Data quality dashboard sent in 5 days after the data collection period completion | - |
| Data verification and back checks | Quality check of submitted data by physical or phone contact with the farmer | Submission of the collected data | DV or BC starts in 10 days after planting/harvest completion | DV implemented using available data |
| Data quality performance tracker | Number of submissions per form per Officer and data gaps | None | Tracker shared and discussed with FFT 10 days after trial completion | - |

Service 3: Weather data monitoring

Client: Field Trials Team/Station team/Trial Owners

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Weather data dashboards | Sharing the submitted data from each device regularly |  | Monthly (10th) |  |
| Weather data integration with trial data | Agreed upon climatic variables are integrated in the shared trial data | Sending request for weather variables to be implemented 1 month before the trial completion | 1 week after data cleaning |  |
| Weather sensors tracking | Maintaining the sensors trackers with up-to-date information | Reporting the device status change immediately | Tracker update 1 day after status change report |  |

Service 4: Data processing and analysis

Client: Trial Owners

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Trials data export, cleaning & hand-over | Sharing clean data with the TO and official confirmation that the data are ready for analysis | NA | One month after trial completion |  |
| Data analysis support | Providing data analysis support as requested by the trial owners | - An alignment meeting is conducted in 2 weeks before the support implementation - Complete the service request form at least one month before the survey implementation | Results are provided within 2 weeks after the request confirmation | No service |
| Maintaining the on-farm trials data inventory matrix | On-farm trials inventory matrix is kept fully up to date, in line with SOP (see SOP tracker), to enable meta-analyses at any time. No row is missing data. Trial names match those in the Report Tracker. The pivot table is set up for use by any TO to search trials. Changes to improve the utility of inventory for meta-analyses are implemented annually. | NA | No data gaps in the inventory matrix. It is updated within 4 weeks of trial completion. | NA |

Service 5: IT Equipment sub-inventory management

Client: INN Department

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Tablets/PCs/Monitors tracking | Maintaining the PCs/tablets trackers with up-to-date information | On-time update of each device status change within 48 Hours | Weekly update of the tracker on Monday | Tracker updated with the available information |
| Keep the devices that are not in use | Keeping all devices that are not being used in the data team office | Managers' Update on the available devices |  |  |
| Tablets general maintenance | Having all tablets maintained twice per year. | Subteam tablets' general maintenance plan | Twice per year | No service |

Service 6: Surveys Implementation

Client: Trial Owners/HTE

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Questionnaire design and explanations | Alignment with TO on the survey objective and questions | - An alignment meeting is conducted in 2 weeks before the survey implementation - Questionnaire translation in English and Kiny | FTT feedback is integrated into the final version 2 days before data collection starts. | The final version of the datasheet is shared but 3 days after the deadline. |
| Phone call Survey implementation | Alignment with TO on the sample size for the phone call | - TO provide the sample size for the phone call (300 maximum farmers) - TO provide a list of farmers to be surveyed with their phone numbers if they are not from the Innovations dataset. - TO provide farmer selection criteria if farmers are from the Innovation dataset - Complete the service request form at least 3 weeks before the survey implementation. Nb: Phone call survey requests are not accepted during DV period( November, December) | - Receiving the survey data within 7 days of working days. - Receiving the cleaned survey data 4 days after phone call completion. | - If the sample size is more than 300 farmers, the survey requires the approval of the Innovation department lead and the data team lead. |

##### 5.3. Inventory team services

Service 1: Inventory management

Clients: Station/Field Trials teams/ Laboratory/Trial Owners/HTE

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Consumables management (CON) | New orders when the Minimum Stock Limit for consumables and trial supplies is reached [materials for inputs packaging, soil/plant samples collection, batteries, ribbons, strings, sacs, etc]; Maintaining updated stock status in CON tracker | - Brand recommendation - Placing an item request by filling out this Form | Quantity available in stock for each item is above the minimum limit, and clients’ requests are fulfilled within 1 day after submission | - No service if the respective Form is not submitted - No service if the respective SOP is not provided - Inventory will use the previously sourced brand if no brand updates are provided |
| Regular measurement materials management (DSE) | Ensuring sufficient buffer stock for replacement; Tracking transfers, availability, and functionality status in the DSE tracker; Calibration regularly | - Determining the stock buffer quantity - Reporting equipment status change within 24 hours using this Form - Equipment calibration SOP - Placing an Equipment request by filling out this Form | - DSE tracker is updated within 24 hours after receiving new equipment or status change report - Clients’ requests are fulfilled within 1 day after submission |  |
| Forecasting (CON & DSE) | Prepare quarterly forecasts for PRO; Aug report to sub-team leads to inform budgeting (specifically for CON and DSE inventories) | NA | Quarterly forecasts submitted to PRO and to INN in Aug by the 15th for budgeting |  |
| Lab equipment and other special materials management (DSE + EUE) | Ordering new equipment and replacements for DSE, with approver green light; executing & tracking any regular maintenance of DSE or EUE equipment; Tracking functionality status in DSE or EUE trackers | - Reporting equipment status change within 24 hours using this Form - Placing an Equipment request by filling out this Form | - EUE tracker is updated within 24 hours after receiving new equipment or a stock status change - Clients’ requests are fulfilled within 1 day after submission |  |
| (Bio-) chemicals management (BCH) | Materials in this inventory must be tracked, with all required fields completed; appropriate storage & any other required handling should be researched and executed (with notes in the inventory); disposal should follow the developed protocol. | - Providing seasonal forecasts by [month, date] for A Season and [month, date] for B Season - Chemicals handling and disposal SOP - Placing an Equipment request by filling out this Form | - BCH tracker is updated within 24 hours after receiving a new item or a stock status change - Clients’ requests are fulfilled within 1 day after submission |  |
| Seeds inventory management (SED) | Maintaining an updated SED tracker with available quantities and performing germination tests and seed weight. | - Providing information on the delivered product within 12 hours after the Inventory team classification request | - SED tracker is updated within 24 hours after receiving a new item or a stock status change - submission of seed samples (excluding newly imported seed) to Seed Team for germination tests by __ for A season and ___ for B season (target is to initiate tests 8 weeks before data is needed). | Trackers are updated with the information that the Inventory team can find |
| Materials receiving | Acknowledging orders receipt at the WH => Weight, count, inspect quality, update appropriate trackers with maximum details |  | The respective tracker is updated within 24 hours |  |
| Inventories auditing | Annual verification of all materials across all inventories and bringing the report (error frequency, materials lost, materials disposed) to the bi-weekly meeting | NA | Annual inventory auditing is done at [month, date], and the report is shared with INN within 2 weeks after the audit | NA |

Service 2: Input sourcing and packaging

Client: Trial Owners

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Sourcing seasonal trial inputs from Logistics | Ordering fertilizers and seed varieties available in the LOG Warehouses | Completing the input calculation by | Inputs are delivered 2 weeks after inputs calculation | No service (?) |
| Inputs packaging | Packaged type and quantity per experimental unit, farmer, and trial site are accurate | - Packaging instructions are provided to the Inventory team 1 week before the planned packaging date. | 100% of inputs packaged according to the instructions |  |

##### 5.4. Laboratory team services

Service: Samples handling & analysis and other experimental procedures

Clients: Trial Owners

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Samples and Results tracking & storage | Tracking the submission of samples for each season and timely troubleshooting issues with the submitting team; managing an overview dashboard. Maintain a historical dataset of results for future use. Secure storage at the required temperature according to TO needs. | - Submit the analysis request using this Form by clearly indicating: the type of sample; season/month of collection; parameters; and number of samples/parameter; - Clear sample coding and labelling (refer to this template for basic information) | - 100% of samples recorded within 3 working days of arrival - Results dataset updated within 24 hours after results are available | No service |
| Soil samples analysis by in-house | Performing in-house soil analysis and handing over the results to the TO. Supported parameters now: Soil moisture and Soil pH. |  | Results handed over to TO in 4 weeks after receiving samples |  |
| Plant samples analysis by in-house | Performing plant samples analysis and handing over the results to the TO. Supported parameters now: Dry matter (%) |  |  |  |
| Samples analysis by external provider | Processing and sending the samples (soil, plant, compost, fertiliser) to the approved external lab; regular follow-up to ensure results are ready at the agreed-upon timeline; ensure the needed parameters are analyzed using the appropriate method. Integrate results into central tracker and, if required, trial datasheet (consult TO). Conducting periodic cross-calibration with multiple external providers. |  | - Samples are sent to the Lab in 4 weeks after reception; and - Results are available in 3 months after sending samples |  |
| Samples disposal | Adequate storage of the samples during the agreed-upon period. |  | Samples kept during xxx months according to this SOP |  |
| Execution of other ad-hoc lab experiments & procedures | Supported service now: - Insect identification - Microbial enumeration (plating) or identification (microscopy) - Seed pellet/coating germination tests - Dilution of chemicals or inoculants - Testing accuracy or precision of sensors/analytical devices (e.g. reflectometer, pH rapid kit, etc) - scoop size calibrations (usually every 2 years) |  | Results are available by: according to the timeline agreed with requestor Scoop size calibrations |  |

##### 5.5. Station trials team’s services

Service: Trial implementation

Client: Trial owners

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Rotation plans | Ensuring homogeneous soil conditions per block, considering zoning/rotations, and treatment layout | The trial plan is complete, and the sample size is well defined by: June 30th (A Season); November 25th (B Season); March 15th (C Season). | - Pre-mortem provided within 2 weeks after communicating the trial. - ?? | Service provided after the approval of the Sub-team and INN Leads |
| Implementing treatment randomization | Adequate treatment sequencing in plots as indicated by the provided randomization. P1: TO does randomisation; P1 does plot allocation | - Protocols development task complete - protocol delivered in 2 weeks before the trial starts - Data collection sheets with treatments randomized are delivered 5 days before the trial starts | 100% of treatments are allocated correctly in the plots and blocks | Service is provided but later than expected, or with a low sample size. In this case, the implementing team is not held responsible. |
| Input distribution to stations | Getting inputs delivered to their respective stations | Inputs and special trial supplies are delivered to the WH by: July 30th (A Season); January 5th (B Season); April 15th (C Season). | Aug 15th (A Season); January 15th (B Season); April 30th (C Season) |  |
| Timely implementation | Each activity is completed on time and according to the agreed-upon protocol | - Protocol is delivered 2 weeks before the activity starts - Special measurement materials sourcing done 10 days before the measurement, with protocol and training | Not later than 3 days from the planned time |  |
| Quantitative/qualitative data collection | Collecting agreed-upon data accurately and on time | The datasheet is complete (100%) in 5 days before the trial starts | 2 days after data recording | Data are collected only with the blocks that are still in the right data collection window |
| Data submission | Timely submission of collected data |  | 5 days after data recording |  |
| Weather sensors installation and Security | Ensuring continuous weather data collection and submission. This is considered “data submission” if a manual tool is being used. | - Providing a working weather sensor and installation protocol | 100% of sensors are installed according to the protocol Sensor troubleshooting support is provided within 2 days after the request. | No service |
| Soil/plant samples collection | Soil and plant samples are collected according to an agreed-upon protocol, well labeled, and well kept | - Protocol is delivered 2 weeks before the soil sampling activity starts | Soil/plant samples are collected on 100% of plots | Soil samples or plant samples will be collected on the blocks that are still in the right condition at the time of protocol availability |
| Soil/plant samples submission | Soil samples are delivered to the Laboratory team on time |  | Samples are submitted to the Laboratory not later than 10 days for soil samples and 10 days for plant samples |  |
| Execution progress update | Trials implementation updates are provided regularly in an agreed-upon format | NA | Execution updates are shared 5 days after each trial period completion. | NA |
| Data cleaning & handover | Official confirmation that the data are ready for analysis |  | 10 working days after final station data upload |  |
| Observations + Lessons learnt consolidation at the end of the trial | Consolidating the observations and lessons learnt by the implementing team and delivering that information to the TO for mutual learning |  | 20 working days after the cleaned data handover |  |

##### 5.6. Field trials teams’ services

Service: Trial implementation

Client: Trial owners

| Task | Expectation | Client’s responsibilities | Highest level of service | Level of service if requirements are not fully met |
| --- | --- | --- | --- | --- |
| Farmers' recruitment | Enrolling the required sample size of trial participants and fields based on agreed-upon criteria and confirming consent. | The trial plan is complete, and the sample size is well defined by: June 30th (A Season); November 25th (B Season); March 15th (C Season). | - Pre-mortem provided within 4 weeks after communicating the trial (bandwidth, space, protocols, tools). - 100% of farmers who completed the trial and well-selected fields | Service provided after the approval of the Sub-team and INN Leads |
| Implementing treatment randomization | Adequate treatment sequencing in plots as indicated by the provided randomization. P2: FTT does randomisation | - Protocols development task complete - protocol delivered in 2 weeks before the trial starts - Data collection sheets with treatments randomized are delivered 5 days before the trial starts | 100% of treatments are allocated correctly in the plots and blocks | Service is provided but later than expected, or with a low sample size. In this case, the implementing team is not held responsible. |
| Input distribution to stations/farmers | Getting inputs delivered to their respective stations/regions/farmers | Inputs and special trial supplies are delivered to the WH by: July 30th (A Season); January 5th (B Season); April 15th (C Season). | Inputs are delivered at their respective sites by: Aug 15th (A Season); January 15th (B Season); April 30th (C Season). |  |
| Timely implementation and effective farmers' involvement | Each activity is completed on time and according to the agreed-upon protocol, with full ownership by the farmer. | - Protocol is delivered 2 weeks before the activity starts - Special measurement materials sourcing done 10 days before the measurement, with protocol and training | 98% of protocol compliance 95% of farmers who understood the trial activities (DV) |  |
| Quantitative/qualitative data collection | Collecting agreed-upon data accurately and on time | The data collection sheet (Form) draft is shared with the FTT 1 week before data collection starts. | 100% of data completeness after each data collection Form | Data are collected only with the blocks/farmers that are still in the right data collection window |
| Data submission | Timely submission of collected data |  | Data are available on the server within 5 days after activity completion in the field/by farmers |  |
| Weather sensors installation and Security | Ensuring continuous weather data collection and submission. This is considered “data submission” if a manual tool is being used. | - Providing a working weather sensor and installation protocol | 100% of sensors are installed according to the protocol Sensor troubleshooting support is provided within 2 days after the request. | No service |
| Soil/plant samples collection | Soil and plant samples are collected according to an agreed-upon protocol, well labeled, and well kept | - Protocol is delivered 2 weeks before the soil sampling activity starts | Soil/plant samples are collected on 100% of plots/farmers | Soil samples or plant samples will be collected on the blocks/farmers who are still in the right condition at the time of protocol availability |
| Soil/plant samples submission | Soil samples are delivered to the Laboratory team on time |  | Samples are submitted to the Laboratory not later than 20 days for soil samples and 10 days for plant samples |  |
| Execution progress update | Trials implementation updates are provided regularly in an agreed-upon format | NA | Execution updates are shared 5 days after each trial period completion. | NA |
| Observations + Lessons learnt consolidation at the end of the trial | Consolidating the observations and lessons learnt by the implementing team and delivering that information to the TO for mutual learning |  | The lesson learnt report is submitted to the TO within 15 days after data handover |  |

#### 6. Communication and Additional SLAs

- Clarifications/Issues (from Implementing or Support teams to Trial Owners): Once an issue is found that needs immediate troubleshooting, the implementing team or supporting team has to raise that to the Trial Owner immediately to find the solution together. In such instances, it is advised to call the Trial owner directly.

- Implementing or Data teams <> Trial Owners syncs:

  - The primary aim for these conversations is to align on the protocols or datasheets for the next activities. They are forward-looking rather than backward-looking. To foster proactivity and ownership, they are primarily organized by the implementing or support teams rather than the trial owners, since these teams are the ones who develop their execution calendars. Trial owners are requested to make time and respond promptly to the requests from these syncs. Organizers are expected to schedule these syncs regularly.

  - The trial owners can organize forward-looking special syncs, aiming to provide an in-depth explanation of a specific protocol. In that case, they should happen early enough to allow ample time for datasheets updates (if necessary) and further alignments by implementing teams at the regional level (usually after alignment between the Coordinator and the TO, the coordinator needs time to communicate and onboard regional implementers on the protocol updates) before the time of actual use of the protocol in the field.

- Field visits by Trial Owners

  - Trial owners have to schedule as many visits as possible to implementing teams throughout the season. According to implementing teams’ feedback, this practice is proven to maximize protocol clarity. In spite of bandwidth limitations, a minimum of two visits (in different trial periods) should be scheduled, and each visit should cover as many sites as possible.

- Bi-weekly INN team meeting: This meeting remains the main platform for alignment on issues related to this SLA or brainstorming about an issue that may arise from a specific trial, in case a group view/contribution is strongly needed.

- Execution progress updates: Each implementing team is expected to develop a format for trial implementation progress updates. The goal is to communicate officially that a specific period is complete, and a summary of the main feedback (ups and downs) related to that specific trial period, and suggested recommendations.

- Feedback on Services: These are opportunities for each team to provide feedback on the quality of services received from its serving parties. These feedbacks are directed to the Department Head and is considered a metric on how INN is complying with this SLA. The time for this feedback is indicated in the Key dates table.

- Additional SLAs

  - Inventory & Laboratory Team SLA specifically addressing soil and plant analyses (link)

  - INN <> SIC SLA specifically addressing the VCU services (link)

- SOPs: The SLA mentions some SOPs that may not yet be developed. Sub-teams should annually plan the development of new SOPs and training of staff that is needed for service fulfillment.

#### 7. Escalation Procedure

Under this SLA, escalation will occur after an SLA breach has occurred. Its aim is either to resolve an issue (in most cases) or gain sufficient understanding of the cause of the breach, or to seek a session to identify measures to be taken in future seasons. Escalation will always be done by Email; the guidelines are below:

- Who escalates: Escalation is initiated by the served party in case the serving party failed to meet the agreed target.

- How: To enable tracking, escalation is done by Email and always has the term “Escalation - [Issue and concerned team]” in the subject. An example is presented below:

  - Service = Trial planning on time

  - Issue = Trial implementation service request received later than 5 days after the indicated deadlines.

  - Email’s Subject: Escalation – Addressing [the trial name] implementation request by the station/field team

- To whom: The table below shows who to escalate to depending on the serving team. Regular interaction contact is the first contact person when requesting the service from that team.

| Serving team | Regular interactions contactee | Write escalation email to: |
| --- | --- | --- |
| Trial owners | Specific trial owner | Trial owner’s manager + INN Lead |
| Station | Stations Coordinator | P1 Sub-team Lead + INN Lead |
| Field trials team | Field Trials Team Coordinator | P2 Sub-team Lead + INN Lead |
| Data team | Data Team Coordinator | Data Team Lead + INN Lead |
| Lab & Inventory | Lab & Inventory Coordinator | Lab & Inv team Lead + INN Lead |

#### 8. Review and Amendment

This SLA is reviewed annually or as needed to ensure its continued relevance and effectiveness. Any amendments must be agreed upon by the respective Sub-team Leads and the Department Lead.

#### 9. Signatures

James Ellison

[Signature]

Agriculture Innovations Department Lead

Jean Honore Ndorimana							Jean De La Paix Ahimana

[Signature]									[Signature]

Sub-team Lead, Station Trials & HTE Teams					Stations Team Coordinator

Elyse Tuyishime						Fidele Habimana			Josephine Nishimwe

[Signature]						[Signature]				[Signature]

Sub-team Lead, On-Farm Trials Team & Data Team	Field Trials Team Coordinator		Data Team Coordinator

[Name]

[Signature]

Sub-team Lead, Inventory & Laboratory Team

Thierry Niyigena

Lucky Regis Usenga

Lucie Kayitesi

Trial Owner(s)

Special materials are materials that are not regularly used by the team and require to be sourced/introduced.

These are materials we need to keep the minimum stock for and for measurements materials, sub-teams should have similar brands

Diverse sources should be used (e.g. Global Knowledge Hub, interviews with stakeholders, MEL data, surveys, & literature review). In case multiple options exist, a prioritisation technique should be applied (e.g. weighted criteria analysis). Critical path (currently we use Clickup) should show activities, key results/milestones, responsible persons & timelines.